Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 9 March 2026 |
| --- | --- |
| Team ID | PNT2026TMID699d5fb63074df695bbbb03f |
| Project Name | Project - Stock trading |
| Maximum Marks | 8 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register for the application by entering my email, password, and confirming my password. | 2 | High | Shreya Dhaytonde |
| Sprint-1 | Registration | USN-2 | As a user, I will receive confirmation email once I have registered for the application | 1 | High | Shreaysh Chudiwal |
| Sprint-1 | Login | USN-3 | As a user, I can log into the system using my email and password. | 2 | High | Shreya Dhaytonde |
| Sprint-1 | Dashboard | USN-4 | As a user, I can view my dashboard showing balance and portfolio summary. | 3 | High | Shreaysh Chudiwal |
| Sprint-2 | Stock Listing | USN-5 | As a user, I can view available stocks in the market. | 2 | High | Shreya Vazarkar |
| Sprint-2 | Stock search | USN-6 | As a user, I can search stocks by name or symbol. | 3 | Medium | Shreya Dhaytonde |
| Sprint-2 | Buy stocks | USN-7 | As a user, I can buy stocks using virtual funds. | 3 | High | Shreya Vazarkar |
| Sprint-2 | Sell stocks | USN-8 | As a user, I can sell stocks that I own. | 2 | High | Shreaysh Chudiwal |
| Sprint-3 | Portfolio | USN-9 | As a user, I can track my portfolio performance. | 2 | High | Shreya Dhaytonde |
| Sprint-3 | Transaction History | USN-10 | As a user, I can view my past stock transactions. | 3 | High | Shreya Vazarkar |
| Sprint-3 | Watchlist | USN-11 | As a user, I can add stocks to my watc22hlist.. | 3 | Medium | Shreya Vazarkar |
| Sprint-3 | charts | USN-12 | As a user, I can view stock price charts and historical trends. | 3 | High | Shreya Vazarkar |
| Sprint-4 | Admin panel | USN-13 | As an admin, I can add, edit, or remove stocks. | 3 | High | Shreya Dhaytonde |
| Sprint-4 | User management | USN-14 | As an admin, I can manage user accounts. | 2 | Medium | Shreaysh Chudiwal |
| Sprint-4 | security | USN-15 | The system provides secure authentication using JWT. | 3 | Medium | Shreya Dhaytonde |
| Sprint-4 | Notifications | USN-16 | Users receive notifications for trades and updates. | 2 | Low | Shreaysh Chudiwal |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 15 Mar 2026 | 20 Mar 2026 | 20 | 20 Mar 2026 |
| Sprint-2 | 20 | 6 Days | 22 Mar 2026 | 27 Mar 2026 | – | – |
| Sprint-3 | 20 | 6 Days | 29 Mar 2026 | 03 Apr 2026 | – | – |
| Sprint-4 | 20 | 6 Days | 05 Apr 2026 | 10 Apr 2026 | – | – |

Velocity:

Imagine we have a 10-day sprint duration, and the velocity of the team is 20 story points per sprint.

Average velocity per day is calculated as:

AV = Sprint Story Points / Sprint Duration

AV = 20 / 10 = 2 story points per day

This means the team can complete 2 story points per day on average.

Burndown Chart:

A Burndown Chart is a graphical representation of work remaining versus time in a sprint.

It helps teams:

Track the remaining tasks in a sprint

Monitor team progress

Ensure project completion within the sprint deadline

In the SB Stocks project, the burndown chart will track progress of features such as

User registration and login

Stock listing and search

Buying and selling stocks

Portfolio tracking

Watchlist management

Admin stock management

By monitoring sprint progress using the burndown chart, the team can identify delays early and adjust tasks to ensure successful completion of the project.

Reference:

https://www.atlassian.com/agile/project-management https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software https://www.atlassian.com/agile/tutorials/epics https://www.atlassian.com/agile/tutorials/sprints https://www.atlassian.com/agile/project-management/estimation https://www.atlassian.com/agile/tutorials/burndown-charts